## 2026 spending V2 29_05_2026
Budget 2026 NEXT GEN | TOTAL | BUDGET | Designation | 2026
| 6125 | 6125 |  | J | F | M | A | M | J | J | A | S | O | N | D
HI ZEP | 725 | 725 | VX/RO/VM | 65.0641 | 65.0641 | 65.0641 | 65.0641 | 65.0641 | 65.0641 | 65.0641 | 9.2949 | 65.0641 | 65.0641 | 65.0641 | 65.0641
HI ZEPE SWH | 365 | 365 | VX | 32.7564 | 32.7564 | 32.7564 | 32.7564 | 32.7564 | 32.7564 | 32.7564 | 4.6795 | 32.7564 | 32.7564 | 32.7564 | 32.7564
AC | 650 | 200 | SEGULA |  |  | 20.5128 | 20.5128 | 20.5128 | 20.5128 | 20.5128 | 15.3846 | 20.5128 | 20.5128 | 20.5128 | 20.5128
|  | 200 | TMC | 17.9487 | 17.9487 | 17.9487 | 17.9487 | 17.9487 | 17.9487 | 17.9487 | 2.5641 | 17.9487 | 17.9487 | 17.9487 | 17.9487
|  | 250 | SECTOR | 22.4359 | 22.4359 | 22.4359 | 22.4359 | 22.4359 | 22.4359 | 22.4359 | 3.2051 | 22.4359 | 22.4359 | 22.4359 | 22.4359
CO DESIGN | 1650 | 500 | BOSCH | 2026 M: 250; 2026 A: 250
|  | 260 | ZF | 2026 O: 260
|  | 140 | ACCELERA | 2026 A: 80; 2026 S: 60
|  | 500 | ELCOM | 2026 M: 250; 2026 S: 250
|  | 100 | UPC | 2026 D: 100
|  | 150 | MPE | 2026 D: 150
AS | 35 | 35 |  | 2026 O: 35
FPT | 1000 | 1000 |  | 2026 M: 500; 2026 J: 250; 2026 O: 250
MATERIAL | 100 | 100 |  | 2026 S: 16; 2026 D: 84
INTERCOMPANY | 1600 | 250 | ALTRASWH | 2026 M: 97; 2026 A: 50; 2026 A: 103
|  | 300 | POWER ELEC | 2026 A: 26; 2026 J: 50; 2026 S: 224
|  | 480 | BATTERIES TEAM | 2026 A: 20; 2026 J: 50; 2026 A: 180; 2026 O: 230
|  | 50 | H2 ECO | 2026 J: 36; 2026 S: 14
|  | 170 | BEV ECO | 2026 M: 57; 2026 A: 26; 2026 S: 87
|  | 300 | HV SYSTEM | 2026 M: 80; 2026 A: 50; 2026 S: 170
|  | 50 | FACILITIES | 2026 S: 50
|  |  | SUB TOTAL | 138.2051 | 138.2051 | 892.7179 | 330.7179 | 658.7179 | 294.7179 | 408.7179 | 648.1282 | 1029.7179 | 933.7179 | 158.7179 | 492.7179
|  |  |  | 105.4487 | 105.4487 | 762.9615 | 247.9615 | 625.9615 | 261.9615 | 375.9615 | 540.4487 | 996.9615 | 900.9615 | 125.9615 | 459.9615
|  |  | CUMUL | 138.2051 | 276.4103 | 1169.1282 | 1499.8462 | 2158.5641 | 2453.2821 | 2862 | 3510.1282 | 4539.8462 | 5473.5641 | 5632.2821 | 6125
|  |  | HI | 97.8205 | 97.8205 | 97.8205 | 97.8205 | 97.8205 | 97.8205 | 97.8205 | 13.9744 | 97.8205 | 97.8205 | 97.8205 | 97.8205
|  |  | AC | 40.3846 | 40.3846 | 60.8974 | 60.8974 | 60.8974 | 60.8974 | 60.8974 | 21.1538 | 60.8974 | 60.8974 | 60.8974 | 60.8974
|  |  | CODESIGN/AS | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 330 | 310 | 295 | 0 | 250
|  |  | FPT | 0 | 0 | 500 | 0 | 0 | 0 | 250 | 0 | 0 | 250 | 0 | 0
|  |  | INTERCOMPANY | 0 | 0 | 234 | 172 | 0 | 136 | 0 | 283 | 545 | 230 | 0 | 0
|  |  | MATERIAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 84

## 2026 spending
Budget 2026 NEXT GEN | TOTAL | BUDGET | Designation | 2026
| 6125 | 6125 |  | J | F | M | A | M | J | J | A | S | O | N | D
HI ZEP | 725 | 725 | VX/RO/VM | 65.0641 | 65.0641 | 65.0641 | 65.0641 | 65.0641 | 65.0641 | 65.0641 | 9.2949 | 65.0641 | 65.0641 | 65.0641 | 65.0641
HI ZEPE SWH | 365 | 365 | VX | 32.7564 | 32.7564 | 32.7564 | 32.7564 | 32.7564 | 32.7564 | 32.7564 | 4.6795 | 32.7564 | 32.7564 | 32.7564 | 32.7564
AC | 650 | 200 | SEGULA |  |  | 20.5128 | 20.5128 | 20.5128 | 20.5128 | 20.5128 | 15.3846 | 20.5128 | 20.5128 | 20.5128 | 20.5128
|  | 200 | TMC | 17.9487 | 17.9487 | 17.9487 | 17.9487 | 17.9487 | 17.9487 | 17.9487 | 2.5641 | 17.9487 | 17.9487 | 17.9487 | 17.9487
|  | 250 | SECTOR | 22.4359 | 22.4359 | 22.4359 | 22.4359 | 22.4359 | 22.4359 | 22.4359 | 3.2051 | 22.4359 | 22.4359 | 22.4359 | 22.4359
CO DESIGN | 1650 | 500 | BOSCH | 2026 M: 250; 2026 J: 250
|  | 400 | ZF | 2026 J: 400
|  | 500 | ELCOM | 2026 A: 250; 2026 S: 250
|  | 100 | UPC | 2026 S: 100
|  | 150 | MPE | 2026 S: 150
AS | 35 | 35 |  | 2026 O: 35
FPT | 1000 | 1000 |  | 2026 M: 500; 2026 J: 250; 2026 O: 250
MATERIAL | 100 | 100 |  | 2026 S: 16; 2026 D: 84
INTERCOMPANY | 1600 | 250 | ALTRASWH | 2026 M: 150; 2026 A: 100
|  | 300 | POWER ELEC | 2026 M: 150; 2026 S: 150
|  | 480 | BATTERIES TEAM | 2026 M: 100; 2026 J: 200; 2026 O: 180
|  | 50 | H2 ECO | 2026 M: 50
|  | 170 | BEV ECO | 2026 M: 80; 2026 J: 90
|  | 300 | HV SYSTEM | 2026 M: 150; 2026 J: 150
|  | 50 | FACILITIES | 2026 S: 50
|  |  | SUB TOTAL | 138.2051 | 138.2051 | 1538.7179 | 408.7179 | 208.7179 | 558.7179 | 1098.7179 | 135.1282 | 874.7179 | 623.7179 | 158.7179 | 242.7179
|  |  |  | 105.4487 | 105.4487 | 1505.9615 | 375.9615 | 175.9615 | 525.9615 | 1065.9615 | 130.4487 | 841.9615 | 590.9615 | 125.9615 | 209.9615
|  |  | CUMUL | 138.2051 | 276.4103 | 1815.1282 | 2223.8462 | 2432.5641 | 2991.2821 | 4090 | 4225.1282 | 5099.8462 | 5723.5641 | 5882.2821 | 6125
|  |  | HI | 97.8205 | 97.8205 | 97.8205 | 97.8205 | 97.8205 | 97.8205 | 97.8205 | 13.9744 | 97.8205 | 97.8205 | 97.8205 | 97.8205
|  |  | AC | 40.3846 | 40.3846 | 60.8974 | 60.8974 | 60.8974 | 60.8974 | 60.8974 | 21.1538 | 60.8974 | 60.8974 | 60.8974 | 60.8974
|  |  | CODESIGN/AS | 0 | 0 | 250 | 250 | 0 | 400 | 250 | 0 | 500 | 35 | 0 | 0
|  |  | FPT | 0 | 0 | 500 | 0 | 0 | 0 | 250 | 0 | 0 | 250 | 0 | 0
|  |  | INTERCOMPANY | 0 | 0 | 630 | 0 | 50 | 0 | 440 | 100 | 200 | 180 | 0 | 0
|  |  | MATERIAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 84

## LF 12M
nex | No constit |  |  | LF 12M
| DEMO "Pay by Customer" TbC |  |  | P1 (07/2026) |  | P2 (01/2027) |  | DEMO1 (05/2027) |  | P3 (04/2027) |  | P4 (08/2027) |  | P5 (01/2028) |  | P35 (03/2028) |  | P32 (02/2028)
|  | Piece Price |  | Nb | Cost (k€) | Nb | Cost (k€) | Nb | Cost (k€) | Nb | Cost (k€) | Nb | Cost (k€) | Nb | Cost (k€) | Nb | Cost (k€) | Nb | Cost (k€)
eDrive | E-Axle | 25 |  | 1 | 25 | 1 | 25 | 1 | 25 | 1 | 25 | 1 | 25 | 1 | 25 | 1 | 25 | 1 | 25
ZF Inverter
EST90
| Câbles HV | 5 |  | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5
| BR | 5 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Distribution | Aux Inverter | 2.9 |  | 1 | 2.9 | 1 | 2.9 | 2 | 5.8 | 2 | 5.8 | 2 | 5.8 | 2 | 5.8 |  | 0 |  | 0
| MPE X-Sample | 10 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 10 | 1 | 10
| HVPDU P B1-Sample | 11 |  | 1 | 11 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | +1 for SK7
| HVPDU P B2-Sample | 11 |  |  | 0 | 1 | 11 |  | 0 | 1 | 11 |  | 0 |  | 0 |  | 0 |  | 0 | 2
| HVPDU P C-Sample | 11 |  |  | 0 |  | 0 | 1 | 11 |  | 0 | 1 | 11 | 1 | 11 | 1 | 11 | 1 | 11 | 5
| HVPDU P D-Sample | 11 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
| HVPDU S B-Sample | 12 |  | 1 | 12 | 1 | 12 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 2 | +1 for SK7
| HVPDU S C-Sample | 12 |  |  | 0 |  | 0 | 1 | 12 | 1 | 12 | 1 | 12 | 1 | 12 | 1 | 12 | 1 | 12 | 6
| HVPDU S D-Sample | 12 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0
Charging | Charging Plugs | 1 |  |  | 0 |  | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| UPC | 5 |  | 1 | 5 |  | 0 | 1 | 5 | 1 | 5 |  | 0 |  | 0 |  | 0 | 1 | 5
| MCS | 1 | En plus UPC box |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Panto | 20 |  |  | 0 |  | 0 |  | 0 | 1 | 20 |  | 0 |  | 0 |  | 0 | 1 | 20
| Marge | 5 |  | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5
| Rail | 3 |  | 1 | 3 |  | 0 | 1 | 3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Cooling | BTMS | 5 |  | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5
Control | VMU | 0.5 |  | 1 | 16.5 | 1 | 0.5 | 1 | 0.5 | 1 | 0.5 | 1 | 0.5 | 1 | 0.5 | 1 | 0.5 | 1 | 0.5
Energy | Batteries GEN3 | 12 | 160€ kw/kg | 5 | 60 | 7 | 84 | 5 | 60 | 7 | 84 | 7 | 84 | 7 | 84 |  | 0 |  | 0
| Batteries GEN4 | 30 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 7 | 210 | 5 | 150
[5 empty] | 150.4 |  | 150.4 |  | 139.3 |  | 180.3 |  | 155.3 |  | 155.3 |  | 285.5 |  | 250.5
|  |  |  | Ordered by other dpt | 30 |  | 30
Note on E9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2 -> 1
Note on E18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2 -> 0 Ordered by PE
Note on F25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: +16k€ VMU with Ethernet
Note on E26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 7 -> 5 packs

## LF 18M
| No constit |  |  | LF 18M
| DEMO "Pay by Customer" TbC |  |  | P13 (11/2027) |  | P14 (11/2028) |  | DEMO3(03/2028) |  | P33
| Cancelled TbC | Piece Price |  | Nb | Cost (k€) | Nb | Cost (k€) | Nb | Cost (k€) | Nb | Cost (k€)
eDrive | E-Axle | 25 |  | 1 | 25 | 1 | 25 | 1 | 25 | 1 | 25
ZF Inverter
EST90
| Câbles HV | 5 |  | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5
| BR | 5 |  |  | 0 |  | 0 |  | 0 |  | 0
Distribution | MPE X-Sample | 10 |  | 1 | 10 | 1 | 10 | 1 | 10 | 1 | 10
| HVPDU P B1-Sample | 11 |  |  | 0 |  | 0 |  | 0 |  | 0
| HVPDU P B2-Sample | 11 |  |  | 0 |  | 0 |  | 0 |  | 0
| HVPDU P C-Sample | 11 |  | 1 | 11 | 1 | 11 |  | 0 |  | 0
| HVPDU P D-Sample | 11 |  |  | 0 |  | 0 | 1 | 11 | 1 | 11
| HVPDU S B-Sample | 12 |  |  | 0 |  | 0 |  | 0 |  | 0
| HVPDU S C-Sample | 12 |  | 1 | 12 | 1 | 12 |  | 0 |  | 0
| HVPDU S D-Sample | 12 |  |  | 0 |  | 0 | 1 | 12 | 1 | 12
Charging | Charging Plugs | 1 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| UPC | 5 |  |  | 0 | 1 | 5 | 1 | 5 |  | 0
| MCS | 1 | En plus UPC box |  | 0 |  | 0 |  | 0 |  | 0
| Panto | 20 |  |  | 0 |  | 0 | 1 | 20 |  | 0
| Marge | 5 |  | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5
| Rail | 3 |  |  | 0 | 1 | 3 |  | 0 |  | 0
Cooling | BTMS | 5 |  | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5
Control | VMU | 0.5 |  | 1 | 0.5 | 1 | 0.5 | 1 | 0.5 | 1 | 0.5
Energy | Batteries GEN3 | 12 | 160€ kw/kg |  | 0 |  | 0 |  | 0 |  | 0
| Batteries GEN4 | 30 |  | 8 | 240 | 8 | 240 | 8 | 240 | 8 | 240
[5 empty] | 315.5 |  | 323.5 |  | 340.5 |  | 315.5

## LF 10M
| No constit |  |  | LF 10M
| DEMO "Pay by Customer" TbC |  |  | P26 (04/2029) |  | DEMO4 (05/2029)
|  | Piece Price |  | Nb | Cost (k€) | Nb | Cost (k€)
eDrive | E-Axle | 25 |  | 1 | 25 | 1 | 25
ZF Inverter
EST90
| Câbles HV | 5 |  | 1 | 5 | 1 | 5
| BR | 5 |  |  | 0 |  | 0
Distribution | MPE X-Sample | 10 |  | 1 | 10 | 1 | 10
| HVPDU P Serial | 3 |  | 1 | 3 | 1 | 3
| HVPDU S Serial | 3 |  | 1 | 3 | 1 | 3
Charging | Charging Plugs | 1 |  | 2 | 2 | 2 | 2
| UPC | 5 |  |  | 0 |  | 0
| MCS | 1 | En plus UPC box |  | 0 |  | 0
| Panto | 20 |  |  | 0 |  | 0
| Marge | 5 |  | 1 | 5 | 1 | 5
| Rail | 3 |  |  | 0 |  | 0
Cooling | BTMS | 5 |  | 1 | 5 | 1 | 5
Control | VMU | 0.5 |  | 1 | 0.5 | 1 | 0.5
Energy | Batteries GEN3 | 12 | 160€ kw/kg |  | 0 |  | 0
| Batteries GEN4 | 30 |  | 5 | 150 | 5 | 150
[5 empty] | 208.5 |  | 208.5

## IC
| No constit |  |  | LE 12/13M | [7 empty] | LE 10M |  | NF 12/13M | [7 empty] | NF 10M
| DEMO "Pay by Customer" TbC |  |  | P15 (01/2029) |  | P16 (05/2029) |  | DEMO5 Class I (03/2030) |  | DEMO6 Class II (02/2029) |  | P27 (05/2031) |  | P21 (09/2028) |  | P22 (11/2028) |  | P23 (11/2029) |  | DEMO7 13M (01/2030) |  | P28 (04/2031)
|  | Piece Price |  | Nb | Cost (k€) | Nb | Cost (k€) | Nb | Cost (k€) | Nb | Cost (k€) | Nb | Cost (k€) | Nb | Cost (k€) | Nb | Cost (k€) | Nb | Cost (k€) | Nb | Cost (k€) | Nb | Cost (k€)
eDrive | E-Axle | 25 |  | 1 | 25 | 1 | 25 | 1 | 25 | 1 | 25 | 1 | 25 | 1 | 25 | 1 | 25 | 1 | 25 | 1 | 25 | 1 | 25
ZF Inverter
EST90
| Câbles HV | 5 |  | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5
| BR | 5 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Distribution | MPE | 2.9 |  | 1 | 2.9 | 2 | 5.8 | 2 | 5.8 | 2 | 5.8 | 2 | 5.8 | 2 | 5.8 | 2 | 5.8 | 2 | 5.8 | 2 | 5.8 | 2 | 5.8
| HVPDU P Serial | 3 |  | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 3
| HVPDU S Serial | 3 |  | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 3 | 1 | 3
Charging | Charging Plugs | 1 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| UPC | 5 |  |  | 0 | 1 | 5 | 1 | 5 |  | 0 |  | 0 | 1 | 5 |  | 0 |  | 0 |  | 0 |  | 0
| MCS | 1 | En plus UPC box |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1 | 1 |  | 0 |  | 0 |  | 0 |  | 0
| Panto | 20 |  |  | 0 | 1 | 20 | 1 | 20 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Marge | 5 |  | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5
| Rail | 3 |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Cooling | BTMS | 5 |  | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5 | 1 | 5
Control | VMU | 0.5 |  | 1 | 0.5 | 1 | 0.5 | 1 | 0.5 | 1 | 0.5 | 1 | 0.5 | 1 | 0.5 | 1 | 0.5 | 1 | 0.5 | 1 | 0.5 | 1 | 0.5
Energy | Batteries GEN3 | 12 | 160€ kw/kg |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Batteries GEN4 | 30 |  | 7 | 210 | 7 | 210 | 7 | 210 | 7 | 210 | 5 | 150 | 7 | 210 | 7 | 210 | 7 | 210 | 7 | 210 | 5 | 150
[5 empty] | 261.4 |  | 289.3 |  | 289.3 |  | 264.3 |  | 204.3 |  | 270.3 |  | 264.3 |  | 264.3 |  | 264.3 |  | 204.3

## Proto_Plan
2025-10-28 | Next Gen vehicles overview |  |  | Product Offering | [10 empty] | 2026 | [51 empty] | 2027 | [51 empty] | 2028 | [51 empty] | 2029 | [51 empty] | 2030 | [51 empty] | 2031 | [51 empty] | 2032
[15 empty] | T1 | [12 empty] | T2 | [12 empty] | T3 | [12 empty] | T4 | [12 empty] | T1 | [12 empty] | T2 | [12 empty] | T3 | [12 empty] | T4 | [12 empty] | T1 | [12 empty] | T2 | [12 empty] | T3 | [12 empty] | T4 | [12 empty] | T1 | [12 empty] | T2 | [12 empty] | T3 | [12 empty] | T4 | [12 empty] | T1 | [12 empty] | T2 | [12 empty] | T3 | [12 empty] | T4 | [12 empty] | T1 | [12 empty] | T2 | [12 empty] | T3 | [12 empty] | T4 | [12 empty] | T1 | [12 empty] | T2 | [12 empty] | T3 | [12 empty] | T4
[12 empty] | -6193 |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Proj | Hypothesis | Type | Batt Gen | PROTO | Assembly | Material K€ | PE Network Management K€ | Skeleton assembly | VV-Vehicle assembly&procurement | Veh_Amortization | Total cost | Coverd By Demo Budget | Assembly | ID
T - Low Floor
T - Low Floor 12BEV |  | - |  | - | [9 empty] | - | T2 26: PER; T1 6: ER; T2 16: DR; T2 23: G6
TCB0114_Q1 - 12m LF BEV |  | Alpha | GEN3.2 | Proto LF 12m | VM/Vx/AY/RO | 950 | 100 |  | 1535 | 0 | 2585 |  |  | P1 | [6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 |  |  |  | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38
TCB0114_Q1 - 12m LF BEV |  | Purch | - | Proto LF 12m | VM/Vx/AY/RO | [5 empty] | 0 |  |  | P1 | bar: 1 to 17
TCB0114_Q1 - 12m LF BEV |  | Beta | GEN3.2 | Proto LF 12m Wave 2 | VM/Vx/AY/RO | 950 | 100 |  | 1095 | 0 | 2145 |  | 3 months après P1 à confirmer par SIR/maturité Start of assembly Juin | P2 | [18 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 |  |  |  | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 |  | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38
TCB0114_Q1 - 12m LF BEV |  | Purch | - | Proto LF 12m Wave 2 | VM/Vx/AY/RO | [7 empty] | 3 months après P1 à confirmer par SIR/maturité Start of assembly Juin | P2
Demo LF 12m | 1 Demo for Busworld Need for Oct 27 | Beta | GEN3.2 | Proto LF 12m Wave 2 | VM/Vx/AY/RO | 950 | 100 |  | 1023 | 0 | 2073 | -2073 | to be ready for bus world event | Demo | [26 empty] | 1 | 2 | 3 | 4 | 5 |  |  |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 |  | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 35 | 36
TCB0114_Q1 - 12m LF BEV |  | Beta | GEN3.2 | Proto LF 12m Wave 2 | VM/Vx/AY/RO | 950 | 100 |  | 1220 | 0 | 2270 |  | 3 months après P2 | P3 | [39 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
TCB0114_Q1 - 12m LF BEV |  | Beta | GEN3.2 | Proto LF 12m Wave 3 | VM/Vx/AY/RO | 800 | 100 |  | 1070 | 40 | 2010 |  |  | P4 | [52 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 |  |  |  | 31 | 32 | 33 | 34
TCB0114_Q1 - 12m LF BEV |  | Gamma | GEN3.2 | Proto LF 12m Wave 4 | VM/Vx/AY/RO | 400 | 100 |  | 600 | 200 | 1300 |  | part Procurement Proto - Skeleton Wleded by Manufacturing - Proto Supprot for assembly | P5 | [104 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
AC - Program LF | AC - Program | Gamma | GEN4 | Proto LF 12m Wave 4 | VM/Vx/AY/RO | 50 | 20 |  | 600 | 500 | 1170 |  | Proto Support for Assembly | P35 | [108 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
GEN 4 | Battry Gen4 - Second HP Supplier | Gamma | GEN4 | Proto LF 12m Wave 4 | VM/Vx/AY/RO | 200 | 20 |  | 600 | 500 | 1320 |  | Proto Support for Assembly | P32 | [112 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
TCB0114_Q1 - 12m LF BEV |  | PB | GEN3.2 | PB Customers Field test | tbd | 80 |  |  | 300 |  | 380 |  | 100% Manufacturing | P6 | [139 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
TCB0114_Q1 - 12m LF BEV |  | PB | GEN3.2 | PB Customers Field test | tbd | 80 |  |  | 300 |  | 380 |  | 100% Manufacturing | P7 | [141 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
TCB0114_Q1 - 12m LF BEV |  | PB | GEN3.2 | PB Customers Field test | tbd | 80 |  |  | 300 |  | 380 |  | 100% Manufacturing | P8 | [143 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
TCB0114_Q1 - 12m LF BEV |  | PB | GEN3.2 | PB Customers Field test | tbd | 80 |  |  | 300 |  | 380 |  | 100% Manufacturing | P9 | [143 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
TCB0114_Q1 - 12m LF BEV |  | PB | GEN3.2 | PB Customers Field test | tbd | 80 |  |  | 300 |  | 380 |  | 100% Manufacturing | P10 | [145 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
TCB0114_Q1 - 12m LF BEV |  | PB | GEN3.2 | PB Customers Field test | tbd | 80 |  |  | 300 |  | 380 |  | 100% Manufacturing | P11 | [145 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
TCB0114_Q1 - 12m LF BEV |  | PB | GEN3.2 | PB Customers Field test | tbd | 80 |  |  | 300 |  | 380 |  | 100% Manufacturing | P12 | [145 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
TCB0114_Q1 - 12m LF BEV | 8 X PB | PB | GEN3.2 | PB Customers Field test | [6 empty] | 0 |  |  | -
T - Low Floor 18BEV |  | - |  | - | [9 empty] | - | [145 empty] | 10 8 6 6 4 4 4: PER | [5 empty] | G4 | [58 empty] | G6
TCB0114_Q2 - 18m LF BEV | 2nd Heat Pump | Beta | GEN4 | Proto LF 18m Wave 4 | VM/Vx/AY/RO | 1500 | 120 | 120 | 1100 | 0 | 2840 |  | start of assembly 04/2027 - fin de debugg fevrier 2028 | P13 | [68 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 |  |  |  | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 |  | 33 | 34 | 35
TCB0114_Q2 - 18m LF BEV | AC - Program ? | Beta | GEN4 | Proto LF 18m Wave 5 | VM/Vx/AY/RO | 1200 | 120 | 50 | 600 | 0 | 1970 |  | start of assembly 02/2028 - fin de debugg septembre 2028 | P14 | [109 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 |  |  |  | 27 | 28 | 29 | 30 | 31
Demo LF 18m | Demo LF 18m with 2nd Heat Pump Need for Busworld Oct 28 | Beta | GEN4 | Proto LF 18m |  | 1200 | 120 | 50 |  | 0 | 1370 | -1370 | to be ready for bus world event | Demo | bar: 14 to 26
TCB0114_Q2 - 18m LF BEV |  | PB | GEN4 | PB Customers Field test | [6 empty] | 0 |  | 100% Manufacturing | - | [185 empty] | x
TCB0114_Q2 - 18m LF BEV | 3 X PB | PB | GEN4 | PB Customers Field test | [6 empty] | 0 |  | 100% Manufacturing | - | [192 empty] | x
TCB0114_Q2 - 18m LF BEV |  | PB | GEN4 | [10 empty] | -
TCB0114_Q2 - 18m LF BEV | AC program | Gamma | GEN4 | Proto LF 18m |  |  |  |  | 300 | 500 | 800 |  |  | P33
- |  | - |  | - | [6 empty] | 0 |  |  | -
- |  | - |  | - | [6 empty] | 0 |  |  | -
T - Low Floor ExtPO |  | - |  | - | [9 empty] | -
TCB0114_Q3 | Proto Update P4 | RNT |  |  | VM/Vx/AY/RO | 25 | 10 |  | 30 | 40 | 105 |  | Retrofit on P4/P14 then 6 months tests planned on vehicle .Tests with P5 after field test on postponed options | P4
TCB0114_Q3 | Proto Update P14 | RNT |  |  |  | 25 | 10 |  | 30 | 40 | 105 |  |  | P14
TCB0114_Q3 | Proto Update P5 | RNT |  |  |  | 25 | 10 |  | 30 | 40 | 105 |  |  | P5
T - Low Floor 10BEV |  | - | [11 empty] | -
TCB0114_Q4 | 1 Protos build from Scratch during 2029 No Demo into Budget | Gamma | GEN4 | LF 10m | VM/Vx/AY/RO | 150 |  | 0 | 600 | 0 | 750 |  | P26 to be planned after 7 PB 12m start of assembly 04/2029 ready for test octobre 29 | P26 | [169 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |  |  |  | 19
AC - Program LF | AC - Program LF | PB | GEN4 | LF 10m | VM/Vx/AY/RO | 50 | 10 |  | 300 | 500 | 860 |  |  | P34 | [242 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
New Need Demo LF 10m | New ! Need for september 2029 | Gamma | GEN4 | Proto LF 10m | [8 empty] | Assembly to be checked as needed for same dates as P26 | Demo | [169 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |  |  |  | 19
T - Low Entry |  | - | [11 empty] | -
T - Low Entry BEV | [13 empty] | -
TIC0101_Q1 | 2 Protos build from Scratch (2β) during 2028/2029 2 PB bought by PE for tests included Into VH budget No Demo into Budget | Beta | GEN4 | LE 12m -13m LE BEV |  | 800 | 80 | 0 | 550 | 0 | 1430 |  | P15 1st proto 08/2028-Ready for test Juin 2029 | P15 | [138 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 |  | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
TIC0101_Q1 |  | Beta | GEN4 | LE 12m -13m LE BEV |  | 800 | 80 | 0 | 550 | 0 | 1430 |  | P16 Start of assembly 02/2029- Ready for test Dec 2029 | P16 | [161 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 |  |  |  | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
TIC0101_Q1 |  | PB | GEN4 | LE 12m -13m LE BEV |  | 500 | 80 |  | 270 | 0 | 850 |  | 2 X PB P17/P18 Start of assembly 09/2030 -02/2031 | P17 | [242 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 |  | 18 | 19
TIC0101_Q1 | AC - Program | PB | GEN4 | LE 12m -13m LE BEV |  | 50 | 20 |  | 270 | 0 | 340 |  | 2 X PB P17/P18 Start of assembly 09/2030 -02/2031 | P18 | [246 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 |  | 14 | 15 | 16 | 17 | 18 | 19
Demo Class 1 LE 12-13m | 1 Demo paid by customer added during Scheduling workshop Need for Q1 2029 | Beta | GEN4 | Proto LE 12-13m class 1 |  | 800 | 80 | 0 | 750 | 0 | 1630 | -1630 | Assembly to be checked as needed for same dates as class2 &P15 (1st proto) | Demo | [132 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 |  | 24 | 25 | 25 | 26 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
Demo Class 2 LE 12-13m | 1 Demo paid by customer added during Scheduling workshop Need for Q1 2029 | Beta | GEN4 | Proto LE 12-13m class 2 | [5 empty] | 450 | 450 | -450 | Assembly to be checked as needed for same dates as class1&P15 (1st proto) | Demo | [132 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 |  | 24 | 25 | 25 | 26 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
TIC0101_Q1 | PB Customer 12m | PB | GEN4 | 12m | [5 empty] | 450 | 450 |  | Assembly from beginning of January until mid Q2 2031 | New | [260 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
TIC0101_Q1 | PB Customer 13m | PB | GEN4 | 13m | 13m |  |  |  |  | 450 | 450 |  | Assembly from mid Q1 until end of Q2 2031 | New | [266 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
T - Low Entry BEV Ext PO | [13 empty] | -
TIC0101_Q2 | 2 X Update on P17/P18 PB Q1 vehicles | RNT |  | LE Ext PO |  | 25 | 10 |  | 30 |  | 65 |  | Tests on P17/P18 start of test 10/2031 | P17
TIC0101_Q2 | 2 X Update on P17/P18 PB Q1 vehicles | RNT |  | LE Ext PO |  | 25 | 10 |  | 30 |  | 65 |  | Tests on P17/P18 start of test 10/2031 | P18
T - Low Entry BEV 10m |  | - | [11 empty] | -
TIC0101_Q3 | 1 Proto from scratch (1β) 1 in 28 No Demo vehicle | Gamma | GEN4 | LE 10m BEV |  | 150 |  | 0 | 270 | 500 | 920 |  | P27 Start of assembly 08/2030- Ready for test 02/2031 | P27 | [286 empty] | 1 | 2 | 3 | 4 | 5 |  |  |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
AC - Program IC |  | PB | GEN4 | LE 10m BEV |  | 50 | 10 |  | 270 | 0 | 330 |  |  | P31 | [290 empty] | 1 |  |  |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
T - Normal Floor |  | - | [11 empty] | - | [164 empty] | PER ? | [43 empty] | DR
T - Normal Floor BEV | [13 empty] | -
TIC0102_Q1 | 3 Protos build from Scratch (3β) ( 1 Durab Veh) No Demo into Budget + 2 PB | Beta | GEN4 | NF 12m -13m BEV |  | 800 | 80 | 0 | 450 | 0 | 1330 |  | Start of P21 assembly 02/2028- Ready for test 12/2028 | P21 | [110 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 |  |  |  | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
TIC0102_Q1 |  | RNT |  | NF 12m -13m BEV | [8 empty] | Retrofit from beta part to gamma part before field test Q1 2030 | P21
TIC0102_Q1 |  | Beta | GEN4 | NF 12m -13m BEV |  | 800 | 80 | 0 | 450 | 0 | 1330 |  | Start of assembly P22 05/2028- Ready for durability test 03/2029 | P22 | [125 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  |  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 |  | 28 | 29
TIC0102_Q1 |  | Gamma | GEN4 | NF 12m -13m BEV |  | 500 | 80 |  | 450 | 0 | 1030 |  | Start of assembly P23 07/2029- Ready for test 04/2030 functional | P23 | [190 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
TIC0102_Q1 |  | PB | GEN4 | NF 12m -13m BEV |  | 50 | 20 |  | 270 | 0 | 340 |  | PB :Start of assembly P24 11/2030 Ready for Field test 03/2031 | P24 | [252 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
AC - Program IC |  | PB | GEN4 |  |  | 50 | 20 |  | 270 | 0 | 340 |  | PB :Start of assembly P25 11/2030 Ready for Field test 03/2031 | P25 | [255 empty] | 1 | 2 | 3 | 4 |  | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
Demo NF 13m | 1 Demo paid by customer added during Scheduling workshop Need for Q3 2030 | Gamma | GEN4 | Gamma NF 12-13m |  | 50 | 20 |  | 200 | 400 | 670 | -670 | ADD veh for Demo in Class 2 Assembly 02/2030 to be ready for 09/30 | Demo | [205 empty] | 1 | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
T - Normal Floor BEV Ext PO |  | - | [11 empty] | -
TIC0102_Q2 | Update proto | RNT |  | NF BEV Ext PO |  | 25 | 10 |  | 30 |  | 65 |  | Retrofit then 6 months tests planned on vehicle .Tests on postponed options | P24
TIC0102_Q2 | Update proto | RNT |  | NF BEV Ext PO |  | 25 | 10 |  | 30 |  | 65 |  | Retrofit then 6 months tests planned on vehicle .Tests on postponed options | P25
T - Normal Floor BEV 10m |  | - | [11 empty] | -
TIC0102_Q3 | 1 Proto from scratch (1β) 1 in 28 No Demo | Beta | GEN4 | NF 10m BEV 1 |  | 150 |  | 0 | 270 | 500 | 920 |  | Start of assembly 10/2030- Ready for test 04/2031 | P28 | [284 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 |  |  |  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
AC - Program IC | 1 Proto from scratch (1β) 1 in 28 No Demo | PB | GEN4 | NF 10m BEV 1 |  | 50 | 10 |  | 270 | 0 | 330 |  | Start of assembly 10/2030- Ready for test 04/2031 | P29 | [284 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 |  |  |  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
T - Normal Floor |  | - | [11 empty] | - | [164 empty] | PER ? | [43 empty] | DR
T- NG ICE Portage |  | - | [11 empty] | -
ICE | 10m C9 Diesel ZF | Beta | NA | NF 10m ICE C9D |  | 80 | 15 | 0 | 80 | 150 | 325 |  | On Assembly Line | - | [208 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
ICE | 13m C9 DIESEL Voith | Beta | NA | LE 13m ICE C9D |  | 80 | 15 | 0 | 80 | 150 | 325 |  | On Assembly Line | - | [214 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
ICE | 10m C9 CNG Voith | Beta | NA | LE 10m ICE C9G |  | 120 | 15 | 0 | 80 | 150 | 365 |  | On Assembly Line | - | [219 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
ICE | 13m C9 CNG ZF | Beta | NA | NF 13m ICE C9G |  | 120 | 15 | 0 | 80 | 150 | 365 |  | On Assembly Line | - | [225 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |  |  |  | 15 | 16 | 17
ICE | 10m T7 Voith | Beta | NA | LE 10m ICE T7 |  | 80 | 15 | 0 | 80 | 150 | 325 |  | On Assembly Line | - | [231 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  |  |  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
ICE | 12m T7 ZF | Beta | NA | NF 12m ICE T7 |  | 80 | 15 | 0 | 80 | 150 | 325 |  | On Assembly Line | - | [235 empty] | 1 | 2 | 3 | 4 |  |  |  | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
-
T- NG ICE Portage |  | -
TIC0102_Q2 | Update proto | RNT | NA | NF BEV Ext PO |  | 25 | 10 |  | 30 |  | 65 |  | Retrofit on P24/P25 then 6 months tests planned on vehicle .Tests on postponed options | P24/25
Jun. 27
G3
Sep. 27
(Preliminary Design Release) PDR
Sep. 27
G5
G6
G2
July. 28
G3
Dec 30
G5
June. 31
G6
PBuild
Feb. 30
G4
ER
Feb. 30
PBuild
May 31
G5
Aug 31
G6
G4
ER
Feb. 30
Sep. 28
G3
Mar. 27
G2
G2
G3
Dec 30
G5
June. 31
G6
G4
Feb. 30
PBuild
May 31
G5
Aug 31
G6
G4
ER
Feb. 30
Sep. 28
G3
Mar. 27
G2
G2
G3
Dec 30
G5
June. 31
G6
G4
Feb. 30
Note on GS30: GELLY ROMAIN: update RG
Note on GZ31: GELLY ROMAIN: Update RG

## Budget
2026 | 2027 | 2028 | 2029 | 2030